## Project Tasks
Customer Appreciation Event
Goal | Thank loyal customers and strengthen relationships. | [6 empty] | SCHEDULE CHECK
Outcome | Host 30 customers with refreshments and a 5-minute business presentation. | [6 empty] | Final day |  |  | 14
Deadline | Day 14 (two-week planning window). | [6 empty] | Within 14 days? |  |  | ON TRACK
Budget | 500 | [6 empty] | Prep complete day |  |  | 13
Scope | Invitations, on-site event, refreshments, presentation, setup and cleanup. | [6 empty] | Dependency issues |  |  | 0
Team member | Role | Responsibility
Jomar Mena | Project Manager | Coordinate progress, track RSVPs and arrange backup help.
Rebecca Semerad | Budget and Resources Manager | Track spending and approve purchases.
Sahil Prabhakar | Event Coordinator | Arrange venue, food and supplies.
Sagar Prabhakar | Communications and Presentation Lead | Manage invitations and business presentation. | [5 empty] | TWO-WEEK GANTT • inclusive calendar days
[8 empty] | Week 1 | [6 empty] | Week 2
ID | Task | Assigned To | Duration (Days) | Start Day | Finish Day | Status | Depends on (ID) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Dependency check | Named owner
1 | Define event scope and approve plan | Project Manager | 1 | 1 | 1 | Not Started | None | [14 empty] | No predecessor | Jomar Mena | bar: Week 1 1
2 | Confirm free on-site location and time | Event Coordinator | 2 | 2 | 3 | Not Started | 1 | [14 empty] | OK | Sahil Prabhakar | bar: Week 1 2 to Week 1 3
3 | Prepare list of 30 customers | Communications Lead | 2 | 2 | 3 | Not Started | 1 | [14 empty] | OK | Sagar Prabhakar | bar: Week 1 2 to Week 1 3
4 | Get quotes and approve spending plan | Budget Manager | 2 | 4 | 5 | Not Started | 2 | [14 empty] | OK | Rebecca Semerad | bar: Week 1 4 to Week 1 5
5 | Create and send digital invitations | Communications Lead | 2 | 4 | 5 | Not Started | 2, 3 | [14 empty] | OK | Sagar Prabhakar | bar: Week 1 4 to Week 1 5
6 | Prepare 5-minute presentation | Communications Lead | 3 | 5 | 7 | Not Started | 1 | [14 empty] | OK | Sagar Prabhakar | bar: Week 1 5 to Week 1 7
7 | Track RSVPs and send reminders | Project Manager | 5 | 6 | 10 | Not Started | 5 | [14 empty] | OK | Jomar Mena | bar: Week 1 6 to Week 2 10
8 | Confirm attendance and dietary needs | Event Coordinator | 1 | 11 | 11 | Not Started | 7 | [14 empty] | OK | Sahil Prabhakar | bar: Week 2 11
9 | Confirm vendors, supplies and equipment | Event Coordinator | 1 | 12 | 12 | Not Started | 4, 8 | [14 empty] | OK | Sahil Prabhakar | bar: Week 2 12
10 | Rehearse presentation and final team check | Project Manager | 1 | 13 | 13 | Not Started | 6, 9 | [14 empty] | OK | Jomar Mena | bar: Week 2 13
11 | Purchase fresh refreshments | Budget Manager | 1 | 14 | 14 | Not Started | 4, 8, 9 | [14 empty] | OK | Rebecca Semerad | bar: Week 2 14
12 | Set up, host event and clean up | Event Coordinator | 1 | 14 | 14 | Not Started | 10, 11 | [14 empty] | OK • buy before setup | Sahil Prabhakar | bar: Week 2 14
■ = scheduled window, not person-days of effort. Relative Days 1–14; no event date supplied.
Sequence: predecessors finish the prior day, except Day 14 refreshments are bought before event setup.
Schedule control: update status daily. PM reviews progress on Days 4, 7, 10 and 13.
If a task slips: notify the PM that day, assign help and revise the plan within Day 14.
Budget control: record receipts on Budget & Risks; get budget-manager approval before spending.
Event agenda (60 minutes): welcome 10, refreshments 20, presentation 5, Q&A 10, networking 15.
Shared workspace: Excel + OneDrive proposed. All four members need edit access; see collaboration checklist below.
Schedule revision: vendor confirmation takes Day 12; rehearsal Day 13. PM takes RSVPs to balance communications work.
TEAM WORKLOAD REVIEW
Team member | Role | Owned tasks | Window-days (not effort)
Jomar Mena | Project Manager | 3 | 7
Rebecca Semerad | Budget and Resources Manager | 2 | 3
Sahil Prabhakar | Event Coordinator | 4 | 5
Sagar Prabhakar | Communications and Presentation Lead | 3 | 7
Fairness review: PM owns RSVP follow-up; communications owns invitations and the presentation. Budget manager also tracks receipts; all four help on event day. Confirm effort-hours as a group before judging equal workload.
Feasibility: prep finishes Day 13; event Day 14. No full-day buffer follows rehearsal. Current spending $485.00 plus $15.00 reserve; reduce optional work if delays or price increases occur.
Discussion: could late RSVPs, vendor delays or equipment problems block readiness? Review on Days 4, 7, 10 and 13; use backup suppliers and test existing equipment before the event.

## Budget & Risks
Event Budget & Risks
Total budget | 500 |  |  |  | Budget comparison | Class proposal | Current plan
Customers | 30 |  |  |  | Refreshments | 200 | 300
[5 empty] | Invitations | 50 | 45
Item | Quantity | Unit estimate | Planned cost | Actual cost | Decorations and supplies | 75 | 110
Venue (business premises) | 1 | 0 | 0 |  | Presentation materials | 25 | 0
Invitations | 30 | 1.5 | 45 |  | Tax / delivery | 0 | 30
Sandwich / snack portions | 30 | 8 | 240 |  | Contingency / reserve | 150 | 15
Drinks | 30 | 2 | 60 |  | Total | 500 | 500
Plates, cups and napkins | 1 | 35 | 35
Decorations | 1 | 75 | 75 |  | Budget check | WITHIN $500
Estimated taxes / delivery | 1 | 30 | 30
Presentation (existing equipment) | 1 | 0 | 0 |  | Current itemized plan retained: $485.00 spending + $15.00 reserve. Planning estimates only; confirm quotes. Class proposal is shown for comparison.
Planned spending |  |  | 485
Unallocated reserve |  |  | 15
Actual spending to date |  |  |  | 0
Remaining cash |  |  |  | 500
Planning estimates only. Confirm quotes before purchasing.
Blank actual costs mean not yet entered. Enter each receipt including tax.
Keep the $50 reserve for unexpected costs. Do not exceed $500 total.
Keep the $15.00 reserve for unexpected costs. Do not exceed $500.00 total.
Assumptions: free business venue and existing presentation equipment. Invitation and supplier costs follow the current editable estimates above.
RISK REGISTER • proposed responses
Potential risk | Possible solution | Risk owner | Trigger / checkpoint | Status
Customers do not respond to invitations | PM sends reminders on Days 7 and 9. Communications Lead invites additional customers, subject to venue capacity; confirm final attendance and dietary needs on Day 11. | Jomar Mena / Sagar Prabhakar | Day 7: fewer than 30 confirmed; check again Day 10. | Monitor
Costs exceed the $500 budget | Compare quotes before approval, reduce optional decorations or menu costs, and use the $15.00 reserve only for essentials. Do not commit above $500.00. | Rebecca Semerad | Any quote exceeds its allowance or total forecast exceeds $500. | Monitor
Current reserve: $15.00 versus the class proposal of $150.00. Price changes require early review. Record receipts beside the matching expenses; blank actuals mean not entered.